Wisconsin Environmental Education Board

WEEB 2 (Rev. 9/07) 	Use reverse or additional sheet, if necessary.

|  | BUDGET SUMMARY |  |
| --- | --- | --- |
| Administering Organization Sitka School District | Project Director Sue McWilliams | Telephone Area/No. 222-333-4444 |
| Budget Category Expense | Project Activity | Grant Request Round each item to whole dollars | Match Round each item to whole dollars | Match Type (i.e., monetary, service, or supplies) & Source of Match |
| Salary/Honoraria (Name or Position) (Rate & time period) 9 school forest committee members at $25/hour 1 hour each (July 2009) 5 school forest education plan task force members (includes project director) at $25/hour – meetings outside of district contract time 4 hours each (July 19, 2009) 4 hours each (July 19, 2009) 12 hours each (July 20-21, 2009) 8 hours each (August – November 2009) 2 hours each (December 3, 2009) 2 hours each (December 2009– January 2010) 4 hours each (February 5, 2010) 2 hours each (March 11, 2010) 2 hours each (August 2010) | Activity Select school forest education plan task force members – meeting on district contract time Overview of school forest education plan outline and example, review existing school forest related documents and resources Conduct site visit with resource manager and Wis. School Forest Ed Specialist First drafting session Information and data collection done independently by task force members Second drafting session Independent information and data collection Final editing, writing, and review Plan district in-service/school forest education plan feedback workshop Complete education plan utilizing input from staff and SF committee and prepare for presentation to the school board | $500 $500 $1,500 $1,000 $250 $250 $500 $250 $250 | $225 | Service – District |
| Project Director during district contracted time at $25/hour 4 hours (April 9, 2010) 45 District staff (including task force members except project director) during contracted time at $20/hour 4 hours each (April 9, 2010) 9 School Forest Committee Members at $25/hr 1 hour (August 2010) Wisconsin School Forest Education Specialist at $20/hour 6 hours (July 19, 2009) 2 hours (July 2009 – December 2010) Natural Resources Manager at $20/hour 4 hours (July 19, 2009) | Conduct district in-service Participate in district in-service, provide feedback on school forest education plan Review and adopt the education plan Provide overview of school forest education plan and conduct site visit with school forest education plan task force members Consultation on data/information collection and plan requirements Conduct site visit with school forest education plan task force members |  | $100 $3,600 $225 $120 $40 $80 | Service – District Service – District Service – committee members Service – LEAF Program Service – LEAF Program Service – DNR |
| Fringe Benefits (Name or Position) (Rate & Percentage of salary) | Activity |  |  |  |
| Travel (mileage, lodging, meals) (Name or no. of people) (Rate & distance, charge) Wisconsin School Forest Education Specialist 150 miles roundtrip X $0.42/mile Natural Resource Manager 25 miles roundtrip X $0.42/mile | Activity Overview of education plan and school forest site visit School forest site visit |  | $63 $11 | Service – LEAF Program Service – DNR |
| Materials/Supplies (Be specific. Identify & quantify items.) Non-Capital Items: Printing of draft education plan 20 pages X $0.05/page X 50 copies Printing of final education plan 20 pages X $0.05/page X 70 copies Capital Items: | Activity District in-service Distributed to district staff, school board, school libraries, school forest committee |  | $50 $70 | Supply – District Supply – District |
| Other | Activity |  |  |  |
| TOTAL |  | Total Request $ 5000.00 | Total Match $ 4584.00 |  |